## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-05-06 | Done | Data lab Preparation | Relational Databases(Datacamp) | Programming | ILO 5.0: Data Understanding and Preparation | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/42bb21890e3f5aa730e97224ffd7f50fb70996b6/Certificate/Introduction_to_SQL.pdf
2024-05-06 | Done | Data lab Preparation | Installing all the reqirments | Research | ILO 5.0: Data Understanding and Preparation | 1 | 3 | 2 |  | Was reasearching which was the best Postgre Sql to use
2024-05-06 | Done | Max 4 hours tasks | Installing the Vpn | Research | ILO 1.0: Professional Practice | 1 | 1 | 0
2024-05-07 | Done | Max 4 hours tasks | Intermidiate Sql (Datacamp) | Programming | ILO 4.0: Business Understanding | 4 | 5 | 1 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/bb8b10d70fed68676a56e25e21ca6f2b741c6349/Certificate/Intermidiate%20_in_Sql.pdf | The Datacamp was more than the expected
2024-05-07 | Done | Max 4 hours tasks | Joining Data in Sql | Programming | ILO 4.0: Business Understanding | 3 | 3 | 0
2024-05-08 | Done | Max 4 hours tasks | Install a postgres Sql database | Study | ILO 5.0: Data Understanding and Preparation | 3 | 3 | 0
2024-05-08 | Done | Max 4 hours tasks | setting up the reqiurments | Study | ILO 7.0: Deployment | 1 | 1 | 0
2024-05-08 | Done | Max 4 hours tasks | Compare different sql opperations | Study | ILO 5.0: Data Understanding and Preparation | 2 | 2 | 0
|  |  |  | Total Hours |  | 17 | 20 | 3
Week 2
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-05-13 | Done | Max 4 hours tasks | Introduction to Wrehouse(Datacamp) | Programming | ILO 5.0: Data Understanding and Preparation | 4 | 4 | 0
2024-05-14 | Done | Max 4 hours tasks | Section 1 | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 1 | 1 | 0
2024-05-14 | Done | Max 4 hours tasks | Section 2 | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 2 | 3 | 1 |  | The exercise was harde than I thought
2024-05-14 | Planned | Max 4 hours tasks | Section 3 | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 2 | 2 | 0
2024-05-15 | Done | Max 4 hours tasks | Time series in Phyton | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/a56241570b67c728ae5ec1fa13d62454978ab00b/Certificate/Manipulatin_Time_series_Data_in_Phyton.pdf | This was only the first chapters
2024-05-15 | Done | Max 4 hours tasks | Manipulating time series in Phyton | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 4 | 3 | -1
2024-05-15 | Done | Max 4 hours tasks | visualizing teams seris data | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/a56241570b67c728ae5ec1fa13d62454978ab00b/Certificate/Manipulatin_Time_series_Data_in_Phyton.pdf
2024-05-16 | Done | Max 4 hours tasks | Travelling |  |  | 3 | 3 | 0
2024-05-16 | Done | Max 4 hours tasks |  |  |  | 3 | 3 | 0
2024-05-16 | Done | Max 4 hours tasks |  |  |  | 3 | 3 | 0
2024-05-17 | Done | Max 4 hours tasks |  | Programming | ILO 5.0: Data Understanding and Preparation | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-05-17 | Done | Max 4 hours tasks | Updat learning log for week 2 | Evidencing | ILO 5.0: Data Understanding and Preparation | 2 | 2
Max 4 hours tasks
|  |  |  | Total Hours |  | 31 | 31 | 0
Week 3
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-05-21 | Done | Data lab | Market research, problem identification & stakeholder analysis | Study | ILO 4.0: Business Understanding | 4 | 4 | 0
2024-05-21 | Done | Data lab | AI Canvas | Study | ILO 4.0: Business Understanding | 1 | 1 | 0
2024-05-21 | Done | Data lab | Doing My report from Block_B | Study | ILO 2.0: Personal Development & Academic Practice | 3 | 3 | 0
2024-05-21 | Done | Data lab | Installing all the reqirments | Study | ILO 6.0: Modelling, Evaluation, and Iteration | 1 | 1 | 0
2024-05-22 | Done | Max 4 hours tasks | Machine Learning Time series with Python | Workshop | ILO 6.0: Modelling, Evaluation, and Iteration | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/a56241570b67c728ae5ec1fa13d62454978ab00b/Certificate/Manipulatin_Time_series_Data_in_Phyton.pdf
2024-05-22 | Done | Max 4 hours tasks | Block C ressubmission section 3.7 | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 2 | 2 | 0 |  | This is the Mlp from Scratch from Last Block
2024-05-22 | Done | Max 4 hours tasks | Block C comments | Evidencing | ILO 6.0: Modelling, Evaluation, and Iteration | 2 | 2 | 0 |  | I did not provide enough comments while
2024-05-22 | Done |  | Presentation (Project Proposal) | Planning
2024-05-23 | Done | Max 4 hours tasks | stand up | Study | ILO 1.0: Professional Practice | 0.5 | 0.5 | 0
2024-05-23 | Done | Max 4 hours tasks | Guest lecture | Lecture | ILO 1.0: Professional Practice | 1.5 | 1.5 | 0
2024-05-23 | Done | Max 4 hours tasks | Workshop (Kanban) | Workshop | ILO 1.0: Professional Practice | 1.45 | 2 | 0.55
2024-05-23 | Done | Max 4 hours tasks | Project Proposal | Testing | ILO 6.0: Modelling, Evaluation, and Iteration | 2 | 3 | 1 |  | The guest from AWNB came to our room to watch the presntation and it ended around 17:30
2024-05-24 | Done | Max 4 hours tasks | Installing the Vpn | Debugging | ILO 5.0: Data Understanding and Preparation | 1 | 1 | 0
2024-05-24 | Done | Max 4 hours tasks | Guest lecture | Meeting | ILO 2.0: Personal Development & Academic Practice | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-05-24 | Done | Max 4 hours tasks | Project Proposal | Workshop | ILO 4.0: Business Understanding | 3 | 3
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 28.45 | 30 | 1.55
Week 4
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-05-27 | Done | Max 4 hours tasks | Blcok_C resubmission | Testing | ILO 2.0: Personal Development & Academic Practice | 5 | 5 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai1-adsai-PetarPaskalev232725/blob/104d1edf92de832b3863d2e50e09fb31dc65da7c/CreativeBrief_Petar_Paskalev_232725.ipynb
2024-05-27 | Done | Max 4 hours tasks | Team meeting | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-05-27 | Done | Max 4 hours tasks | Evidencing worklog | Evidencing | ILO 1.0: Professional Practice | 1 | 1 | 0
2024-05-27 | Done | Max 4 hours tasks | Block_B Report | Study | ILO 2.0: Personal Development & Academic Practice | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-05-28 | Done | Data lab | Stand up | Meeting | ILO 1.0: Professional Practice | 0.5 | 0.5 | 0
2024-05-28 | Done | Data lab | Daily Stand up Kanban | Meeting | ILO 1.0: Professional Practice | 1 | 1 | 0
2024-05-28 | Done | Data lab | Eda on the main datasets | Programming | ILO 5.0: Data Understanding and Preparation | 7 | 7 | 0 |  | Me and Mihai aminly worked on that the whole day Shasa did the Project Roadmap
2024-05-29 | Done | Max 4 hours tasks | Daily stand up in Kanban | Meeting | ILO 1.0: Professional Practice | 1 | 1 | 0
2024-05-29 | Done | Max 4 hours tasks | Trying to find how to plot all the different severeties | Study | NA | 3 | 3 | 0
2024-05-29 | Done | Max 4 hours tasks | Plotting all the different severeties (Heatmap) | Programming | ILO 5.0: Data Understanding and Preparation | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-teamwork-t12/blob/465be0109d6769c24760135fdad340c922353ebb/Heatmaps.
2024-05-30 | Done | Max 4 hours tasks | Daily stand up in Kanban | Meeting | ILO 2.0: Personal Development & Academic Practice | 1 | 1 | 0
2024-05-30 | Done | Max 4 hours tasks | Talking more about the project with Mihai | Meeting | ILO 1.0: Professional Practice | 2 | 2 | 0
2024-05-30 | Done | Max 4 hours tasks | Exploring the new dataset | Programming | ILO 5.0: Data Understanding and Preparation | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/main/Project/Week4_dataset/Exploring_dataset.ipynb
2024-05-31 | Done | Data lab | Meeting | Meeting | ILO 2.0: Personal Development & Academic Practice | 0.5 | 0.5 | 0
2024-05-31 | Done | Data lab | Discussing each column with the new dataset | Meeting | ILO 5.0: Data Understanding and Preparation | 5 | 5 | 0
2024-05-31 | Done | Data lab | Retrospective | Meeting | ILO 1.0: Professional Practice | 1 | 1 | 0
0
|  |  |  | Total Hours |  | 36.25 | 36.25 | 0
Week 5
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-06-03 | Done | Max 4 hours tasks | Daily stand up in Kanban | Meeting | ILO 1.0: Professional Practice | 1 | 1 | 0
2024-06-03 | Done | Max 4 hours tasks | Evidencing worklog | Evidencing | ILO 1.0: Professional Practice | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-03 | Done | Max 4 hours tasks | Preprocessed_data | Research | ILO 5.0: Data Understanding and Preparation | 3 | 3 | 0
2024-06-03 | Done | Max 4 hours tasks | Starting the preprocessing pdf file | Study | ILO 6.0: Modelling, Evaluation, and Iteration | 2 | 2 | 0
2024-06-04 | Done | Max 4 hours tasks | Daily stand up in Kanban | Meeting | ILO 1.0: Professional Practice | 0.5 | 0.5 | 0
2024-06-04 | Done | Max 4 hours tasks | Droped the missing values and outliers | Programming | ILO 5.0: Data Understanding and Preparation | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-04 | Done | Max 4 hours tasks | Applied Encoding, Standardizing and SMOTE on the dataset | Programming | ILO 5.0: Data Understanding and Preparation | 3 | 3 | 0
2024-06-05 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-05 | Done | Max 4 hours tasks | completed the pdf file for preprocessing | Programming | ILO 5.0: Data Understanding and Preparation | 3 | 3 | 0
2024-06-05 | Done | Max 4 hours tasks | Changed the data a bit to fit the modeling requirements | Programming | ILO 5.0: Data Understanding and Preparation | 4 | 4 | 0
2024-06-05 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-06 | Done | Max 4 hours tasks | Updated the Preprocessing file | Programming | ILO 5.0: Data Understanding and Preparation | 4 | 4 | 0
2024-06-07 | Done | Max 4 hours tasks | Discussing the models we did yesterday |  |  | 2 | 2 | 0
2024-06-07 | Done | Retrospective Session | Attended Retrospective session | Meeting | ILO 1.0: Professional Practice | 1 | 1 | 0 | https://edubuas-my.sharepoint.com/personal/230306_buas_nl/_layouts/15/stream.aspx?id=%2Fpersonal%2F230306%5Fbuas%5Fnl%2FDocuments%2FRecordings%2FCall%20with%20Group%2012%2D20240607%5F161419%2DMeeting%20Recording%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2E5b92724a%2Dd7b2%2D4f3c%2Db0c9%2D7cfc557b6b65&ga=1 | I attended the retrospective session where we talked about how we will move forward with this project as a team, what we did wrong and what we did good.
|  |  |  | Total Hours |  | 31 | 31 | 0
Week 6
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-06-10 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-10 | Done | Max 4 hours tasks | Evidence on trello | Evidencing | ILO 1.0: Professional Practice | 1 | 1 | 0 | https://trello.com/b/CSA8nuw3/block-d-project-group-12
2024-06-10 | Done | Max 4 hours tasks | Trying to make the sphinx doumentation | Study | ILO 7.0: Deployment | 2 | 2 | 0
2024-06-11 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Lecture | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-11 | Done | Max 4 hours tasks | Modelling review | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 3 | 3 | 0
2024-06-11 | Done | Max 4 hours tasks | Doing Random Forest | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-11 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25
2024-06-12 | Done | Max 4 hours tasks | Streamlit code | Programming | ILO 7.0: Deployment | 3 | 3 | 0
2024-06-12 | Done | Max 4 hours tasks | Unit testing | Programming | ILO 7.0: Deployment | 4 | 4 | 0
2024-06-12 | Done | Max 4 hours tasks | comparing best models | Programming | ILO 6.0: Modelling, Evaluation, and Iteration | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-13 | Done | Max 4 hours tasks | Evidencing block_c | Programming | ILO 2.0: Personal Development & Academic Practice | 2 | 2 | 0
2024-06-13 | Done | Max 4 hours tasks | Evidencing block_B | Study | ILO 2.0: Personal Development & Academic Practice | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-13 | Done | Max 4 hours tasks | Giving retakes | Study | ILO 3.0: Legal Framework | 2 | 2 | 0
2024-06-13 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Study | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-14 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-14 | Done | Max 4 hours tasks | Documenting Unit testing | Study | ILO 7.0: Deployment | 5 | 5
2024-06-14 | Done | Max 4 hours tasks | Retrospective wit the team | Debugging | ILO 2.0: Personal Development & Academic Practice | 1 | 1 | 0
|  |  |  | Total Hours |  | 32.25 | 32.25 | 0
Week 7
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-06-17 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-17 | Done | Max 4 hours tasks | Evidenced Ilo 7 on Juoyter Notebook | Evidencing | ILO 7.0: Deployment | 3 | 3 | 0
2024-06-17 | Done | Max 4 hours tasks | Learning Log Ilo 7 | Evidencing | ILO 7.0: Deployment | 3 | 3 | 0
2024-06-18 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Evidencing | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-18 | Done | Max 4 hours tasks | Discussing evidencig with the team | Meeting | ILO 1.0: Professional Practice | 5 | 5 | 0
2024-06-18 | Done | Max 4 hours tasks | Update trello | Evidencing | ILO 1.0: Professional Practice | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-19 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Evidencing | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-19 | Done | Max 4 hours tasks | Project Presentasion | Evidencing | ILO 4.0: Business Understanding | 3 | 3 | 0
2024-06-19 | Done | Max 4 hours tasks | Fill in Jypeter notebook section Ilo 3 | Evidencing | ILO 3.0: Legal Framework | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-20 | Done | Max 4 hours tasks | Attended Kanban Stand Up | Meeting | ILO 1.0: Professional Practice | 0.25 | 0.25 | 0
2024-06-20 | Done | Max 4 hours tasks | Peer review | Testing | ILO 1.0: Professional Practice | 1 | 1 | 0
2024-06-20 | Done | Max 4 hours tasks | Jupyter notebook completion | Evidencing | ILO 4.0: Business Understanding | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai1-adsai-personal-PetarPaskalev232725/blob/c1bf6502f68c687649c8d7f716d56dd9cdba0666/JupyterNotebook_Y1D_2023-24_group_ILOs.ipynb
2024-06-20 | Done | Max 4 hours tasks | Learning log all sections | Evidencing | ILO 4.0: Business Understanding | 3 | 3 | 0
2024-06-21 | Done | Max 4 hours tasks | Exhibition presentation |  |  | 2 | 2 | 0 |  | I like how the team performed in the Ehibition
2024-06-21 | Done | Max 4 hours tasks | Review Exhibition presentation |  |  | 2 | 2 | 0
2024-06-21 | Done | Max 4 hours tasks | Working log |  |  | 3 | 3 | 0
|  |  |  | Total Hours |  | 34 | 34 | 0
|  |  |  | Total Hours |  | 0 | 0 | 0
|  |  |  | Total Hours in this Block |  | 209.95 | 214.5 | 4.55

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.0: Professional Practice | [8 empty] | 0
ILO 2.0: Personal Development & Academic Practice | [8 empty] | 0
ILO 3.0: Legal Framework | [8 empty] | 0
ILO 4.0: Business Understanding | [8 empty] | 0
ILO 5.0: Data Understanding and Preparation | [8 empty] | 0
ILO 6.0: Modelling, Evaluation, and Iteration | [8 empty] | 0
ILO 7.0: Deployment | [8 empty] | 0
NA | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.0: Professional Practice
Unplanned | Meeting | ILO 2.0: Personal Development & Academic Practice | Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!
Blocked | Programming | ILO 3.0: Legal Framework
In-Progress | Research | ILO 4.0: Business Understanding
Done | Testing | ILO 5.0: Data Understanding and Preparation
Delayed | Workshop | ILO 6.0: Modelling, Evaluation, and Iteration
Cancelled | Planning | ILO 7.0: Deployment
| Evidencing | NA
Debugging
Lecture
Study
Unplanned
Distraction
Break